## Sheet1
Section | TASK | Owner | 2020-11-15 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-20 | 2020-12-27 | 2021-01-03 | 2021-01-10 | 2021-01-17 | 2021-01-24 | 2021-01-31 | 2021-02-07 | 2021-02-14 | 2021-02-21 | 2021-02-28 | 2021-03-07 | 2021-03-14 | 2021-03-21 | 2021-03-28 | 2021-04-04 | 2021-04-11 | 2021-04-18 | 2021-04-25 | 2021-05-02 | 2021-05-09 | 2021-05-16 | 2021-05-23 | 2021-05-30 | 2021-06-06 | 2021-06-13 | 2021-06-20 | 2021-06-27
Convolution HW | Initial Design Spec writing
Initial skeleton implementation
Base Version implementation
Final Design spec update
Final version implementation
ASIC feasibility check (synthesis)
Productizing and documenting
Fully Connected HW
Memory Interface
Software
Integration
Milestone
Initial Mannix Design Spec
Official Plan Report
Initial skeleton Integration (Non Functional)
Primary functional test-case (simulation)
Primary functional test-case (FPGA)
Final Mannix Design Spec
Validation Plan release
Final Version release (simulation & FPGA)
ASIC feasibility check (synthesis)
Final documentation and Project Book Release